## Validation Plan Vs. 1
FSR Reference | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Connectivity range | Bluetooth connectivity for input and output is at least 10 meters. | The GrAPE will be in the center of the input and output bluetooth devices. The two devices will start off right next to the GrAPE, but will be drawn farther away until they reach 10 meters. | TESTED | Nicole LoGiudice
3.2.1.2 | Wireless connection stability | Bluetooth connectivity does not drop more than 1 time per 5 minutes. | Bluetooth will be tested 5 times. Each time, the GrAPE will be equally distanced in the middle from the phone and speaker. | TESTED | Nicole LoGiudice
3.2.1.3 | Bluetooth receiver & DAC | Bluetooth receiver receives the audio signal from an external transmitter. | Bluetooth receiver will receive an input via bluetooth from a phone. The receiver output will be connected to a DAC to then output to a speaker. | TESTED | Nicole LoGiudice
3.2.1.4 | ADC & Bluetooth transmitter | Bluetooth transmitter transmits the audio signal to a specified external receiver and it plays. | An ADC will have an analog signal input and an output connected to the bluetooth transmitter. The transmitter will be put into search mode to find all available receivers in the area. The specified receiver will be selected as the desired receiver. | TESTED | Nicole LoGiudice
3.2.1.5 | Frequency channel selection | Each channel is able to manipulate its frequency and nearby frequencies without excessive disruption of neighboring channels. The channels can work in combination with each other and with multi-tone signals. The sliders frequency gain effects are uniform in nature across all 10 bands. | Each channel will be tested individually against its control frequency. If every channel responds with the ability to adjust its set frequency to a consistent gain magnitude higher and lower than feed amplitude, then the signals will be tested with mixed frequencies with the same expectation of results. | UNTESTED | Nathan Finley
3.2.1.6 | Bandwidth | The full range of the tunable frequencies is 0-20kHz. A single channel has a standard deviation from base frequency in which frequencies outside of said standard deviation are not amplified past a certain gain. | The top and bottom channels will be tested in their gain manipulation of the top and bottom frequencies (0 and 20 kHz) to meet the specified amplitude requirements. Intermediate frequencies will also be tested in the bandwidth of their frequency manipulation. | UNTESTED | Nathan Finley
3.2.1.7 | Display Integration | The display shows a menu on a screen (potentially a LCD) and works concurrently with the bluetooth module on the GrAPE. | The display integration will be tested by checking if the display successfully shows a select menu where it displays the available Bluetooth devices to be connected to. | UNTESTED | Antonio Cardona & Nicole LoGiudice
3.2.1.8 | Control Pad for Display | The user-controlled menu allows the user to select and connect to a Bluetooth speaker. The interface has a minimum of 3 buttons: up, down (or left and right) and an enter button. | The menu will be tested by selecting a Bluetooth device on the display and checking if the GrAPE successfully connects to the selected Bluetooth speaker. | IN PROGRESS | Antonio Cardona
3.2.1.9 | Slidable Knobs | The GrAPE will have 10 slidable knobs which alters the gain frequency of the 10 frequency bands. | Individual and group testing of the set of slidable knobs are tested against an expected gain level from the design. | IN PROGRESS | Nathan Finley
3.2.1.10 | Battery Percentage | The GrAPE will include a battery percetange indicator (potentially a set of LEDs). | Charging and discharging the battery. | UNTESTED | Antonio Cardona
3.2.1.11 | Battery Operating Time | The battery operating time of the GrAPE shall last between 1-4 hours. | Operating the GrAPE and recording battery life while in use. | UNTESTED | Antonio Cardona
3.2.2.1 | Size/dimensions | The GrAPE fits within an average sized backpack with pockets that completely zip. | The GrAPE will be placed within a backpack along with any external parts. | UNTESTED | Full Team
3.2.2.2 | Housing material | The material does not interfere with the bluetooths’ connection to meet the 10 meters requirement. | The GrAPE will be tested first through the ‘Connectivity range’ test without the housing. Once passed, the ‘Connectivity range’ test will be performed with the housing. | UNTESTED | Full Team
3.2.3.1.1 | Power Consumption | Rechargeable battery power supplies expected voltage levels according to its specifications. | User multimeter and oscilloscope to validate voltage and current levels. | IN PROGRESS | Antonio Cardona
3.2.3.1.2 | Input voltage (subsystems) | The required voltage levels for all subsystems is met. | Use multimeter to validate input voltage levels. | IN PROGRESS | Antonio Cardona
3.2.4.1 | Thermal Resistance | The GrAPE operates under room temperature conditions (59°-77°F). | Operating the GrAPE under room temperature conditions. | UNTESTED | Full Team
N/A | Full system demo | The GrAPE accepts audio input from a smartphone device via Bluetooth and is able to connect to a speaker via Bluetooth and Aux. The equalizer has at least 10 frequency channels that can be adjusted by slidable knobs and the audio processing and filtering is analog. The GrAPE's design is small enough to fit into a backpack. | Team members will test the GrAPE with a smartphone device and play an audio signal (i.e a song) via Bluetooth through the equalizer onto a speaker via Bluetooth and Aux. | UNTESTED | Full Team

## Complete Validation Plan
FSR Reference | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Connectivity range | Bluetooth connectivity for input and output is at least 10 meters. | The GrAPE will be in the center of the input and output bluetooth devices. The two devices will start off right next to the GrAPE, but will be drawn farther apart, 1 meter at a time, until reaching 20 meters. | IN PROGRESS | Nicole LoGiudice
3.2.1.3 | Bluetooth Receiver | Bluetooth receiver receives the audio signal from an external transmitter and plays the audio for at least 1 hour. | Bluetooth receiver will receive an input via bluetooth from a phone. The receiver output will be connected to a DAC to then output to a speaker. | IN PROGRESS | Nicole LoGiudice
3.2.1.4 | Bluetooth Trasnmitter | Bluetooth transmitter transmits the audio signal to a specified external receiver and plays the audio for at least 1 hour. | An ADC will have an analog signal input and an output connected to the bluetooth transmitter. The transmitter will be put into search mode to find all available receivers in the area. The specified receiver will be selected as the desired receiver. | IN PROGRESS | Nicole LoGiudice
3.2.1.6 | Frequency Response | The frequency range is at least from 0 - 20kHz and at most +/- 5dB. | The Fourier response will be found for the GrAPE from input to output via Bluetooth and Auxilliary. | UNTESTED | Nathan Finley
| Sensitivity | The GrAPE produces a sensitivity of at least 86 dB on all three sliders (left, right, master) | A speaker of at least 86 dB will be a meter away from a sound level meter. A constant audio signal will be played and sweeped from the lowest dB to highest. This will be done by increasing the slider by a quarter of its total length each time. This will be done via Bluetooth and Auxilliary. | UNTESTED | Nathan Finley
| Signal-to-Noise Ratio | The GrAPE has an SNR of at least 60 dB at maximum amplification. | The GrAPE will play a constant audio stream at maximum amplification. Then, will measure the dB noise and desired audio stream to calculate the SNR. This will be done via Bluetooth and Auxilliary. | UNTESTED | Nathan Finley
| Harmonic Distortion | The GrAPE produces a harmonic distortion of less than or equal to 0.7. | The GrAPE will connect to a speaker and play a constant audio stream without altering any gains of different frequencies at a volume of 80 dB. The harmonic distortion will be calculated. Then, the same speaker will play the same audio stream without the GrAPE. The harmonic distortion will be calculated again. The two data sets will be compared to find the harmonic distortion of the GrAPE. This will be done via Bluetooth and Auxilliary. | UNTESTED | Nathan Finley
3.2.1.7 | Display Integration | The display is able to show 20 names of available speakers for connection and connects to the speaker one picks. | 20 different speakers will be in connection mode, all within 10 meters of the GrAPE. The JBL Charge 2 speaker will be the last speaker put into connection mode. One will select the JBL Charge 2 to connect to the GrAPE. The GrAPE will have an audio input and then connect and play the audio stream on the JBL Charge 2 speaker via Bluetooth. This will also be done with two other speakers. | UNTESTED | Antonio Cardona & Nicole LoGiudice
3.2.1.9 | Slidable Knobs | The GrAPE will have 10 slidable knobs which alters the gain frequency of the 10 frequency bands. | Individual and group testing of the set of slidable knobs are tested against an expected gain level from the design. | IN PROGRESS | Nathan Finley
3.2.1.10 | Battery Percentage | The GrAPE will include a battery percetange indicator (potentially a set of LEDs). | Charging and discharging the battery. | UNTESTED | Antonio Cardona
3.2.1.11 | Battery Operating Time | The battery operating time of the GrAPE shall last between 1-4 hours. | Operating the GrAPE and recording battery life while in use. | UNTESTED | Antonio Cardona
3.2.2.1 | Size/dimensions | The GrAPE fits within an average sized backpack with pockets that completely zip. | The GrAPE will be placed within a backpack along with any external parts. | UNTESTED | Full Team
3.2.2.2 | Housing material | The material does not interfere with the bluetooths’ connection to meet the 10 meters requirement. | The GrAPE will be tested first through the ‘Connectivity range’ test without the housing. Once passed, the ‘Connectivity range’ test will be performed with the housing. | UNTESTED | Full Team
3.2.3.1.1 | Power Consumption | Rechargeable battery power supplies expected voltage levels according to its specifications. | User multimeter and oscilloscope to validate voltage and current levels. | IN PROGRESS | Antonio Cardona
3.2.3.1.2 | Input voltage (subsystems) | The required voltage levels for all subsystems is met. | Use multimeter to validate input voltage levels. | IN PROGRESS | Antonio Cardona
3.2.4.1 | Thermal Resistance | The GrAPE operates under room temperature conditions (59°-77°F). | Operating the GrAPE under room temperature conditions. | UNTESTED | Full Team
N/A | Full system demo | The GrAPE accepts audio input from a smartphone device via Bluetooth and is able to connect to a speaker via Bluetooth and Aux. The equalizer has at least 10 frequency channels that can be adjusted by slidable knobs and the audio processing and filtering is analog. The GrAPE's design is small enough to fit into a backpack. | Team members will test the GrAPE with a smartphone device and play an audio signal (i.e a song) via Bluetooth through the equalizer onto a speaker via Bluetooth and Aux. | UNTESTED | Full Team
FSR Reference | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Connectivity range | Bluetooth connectivity does not drop for input and output for at least 10 meters. | The GrAPE will be in the center of the input and output bluetooth devices. The two devices will start off right next to the GrAPE, but will be drawn farther apart, 1 meter at a time, until reaching 20 meters. | UNTESTED | Nicole LoGiudice
3.2.1.3 | Bluetooth Receiver | Bluetooth receiver receives the audio signal from an external transmitter and plays the audio for at least 1 hour. | Bluetooth receiver will receive an input via Bluetooth from a transmitter. The receiver output will be wired to a speaker. The connection will be tested for 2 hours. This will be tested with a total of three different transmitter devices of a different brand. | UNTESTED | Nicole LoGiudice
3.2.1.4 | Bluetooth Transmitter | Bluetooth transmitter transmits the audio signal to a specified external receiver and plays the audio for at least 1 hour. | The Bluetooth transmitter will have an analog input. The transmitter will connect to the JBL Charge 2 speaker via Bluetooth. The connection will the tested for 2 hours. This will also be tested with two other speakers of a different brand. | UNTESTED | Nicole LoGiudice
3.2.1.7 | Display Integration | The display is able to show 20 names of available speakers for connection and connects to the speaker one picks. | 20 different speakers will be in connection mode, all within 10 meters of the GrAPE. The JBL Charge 2 speaker will be the last speaker put into connection mode. One will select the JBL Charge 2 to connect to the GrAPE. The GrAPE will have an audio input and then connect and play the audio stream on the JBL Charge 2 speaker via Bluetooth. This will also be done with two other speakers. | UNTESTED | Antonio Cardona & Nicole LoGiudice
3.2.1.9 | Frequency Response | The frequency range is at least from 0 - 20kHz and at most +/- 3dB using at least 10 slidable knobs. | A signal generator is connected to the input of the GrAPE, and a voltmeter is connected to the output. The frequency of the signal generator is varied over the frequency range of 0 - 20 kHz and any variation in output level is recorded. The maximum variation is set as the +/-. | UNTESTED | Nathan Finley
Maximum Gain
3.2.1.9.1 | Impedance |  |  | UNTESTED | Nathan Finley
3.2.1.9.2 | Signal-to-Noise Ratio | The GrAPE has an SNR of at least 60 dB at maximum amplification. | A signal generator is connected to the input of the GrAPE, and a millivoltmeter is connected to the output. The signal generator is set to 1 kHz and recorded on the millivoltmeter as the signal. The input signal is then removed and the noise is recorded on the millivoltmeter. | UNTESTED | Nathan Finley
3.2.1.9.3 | Crosstalk | At most, a crosstalk of -80dB at 1 kHz. | The signal generator is connected to the input of the GrAPE. The AC millivoltmeter is connected to the audio output and the output level is recorded as the reference level. The AC millivoltmeter is then moved to the output circuit that is to be tested for crosstalk. | UNTESTED | Nathan Finley
3.2.1.9.3 | Total Harmonic Distortion | The GrAPE produces a harmonic distortion of less than or equal to 0.3%. | The signal generator is connected to the input of the GrAPE. The distortion analyzer is connected to the output and will read the THD. The test is repeated for frequencies 0, 1 kHz, 5 kHz, 10 kHz, 15 kHz, and 20 kHz. The test will be completed for minimum, no change, and maximum gain of each frequency bandwidth, left and right, and master volume. | UNTESTED | Nathan Finley
Intermodulation Distortion
3.2.3.1.1 | Power Consumption | Rechargeable battery power supplies expected voltage levels according to its specifications. | User multimeter and oscilloscope to validate voltage and current levels. | UNTESTED | Antonio Cardona
3.2.3.1.2 | Input voltage (subsystems) | The required voltage levels for all subsystems is met. | Use multimeter to validate input voltage levels. | UNTESTED | Antonio Cardona

## Validation Plan Update #3
FSR Reference | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Connectivity range | Bluetooth connectivity does not drop for input and output for at least 10 meters. | The GrAPE will be in the center of the input and output bluetooth devices. The two devices will start off right next to the GrAPE, but will be drawn farther apart, 1 meter at a time, until reaching 20 meters. | PASSED | Nicole LoGiudice
3.2.1.3 | Bluetooth Receiver | Bluetooth receiver receives the audio signal from an external transmitter and plays the audio for at least 1 hour. | Bluetooth receiver will receive an input via Bluetooth from a transmitter. The receiver output will be wired to a speaker. The connection will be tested for 2 hours. This will be tested with a total of three different transmitter devices of a different brand. | PASSED | Nicole LoGiudice
3.2.1.4 | Bluetooth Transmitter | Bluetooth transmitter transmits the audio signal to a specified external receiver and plays the audio for at least 1 hour. | The Bluetooth transmitter will have an analog input. The transmitter will connect to the JBL Charge 2 speaker via Bluetooth. The connection will the tested for 2 hours. This will also be tested with two other speakers of a different brand. | PASSED | Nicole LoGiudice
3.2.1.7 | Display Integration | The display is able to show 8 names of available speakers for connection and connects to the speaker one picks. | At least 2 different speakers will be in connection mode, all within 10 meters of the GrAPE. The JBL Charge 2 speaker will be the last speaker put into connection mode. One will select the JBL Charge 2 to connect to the GrAPE. The GrAPE will have an audio input and then connect and play the audio stream on the JBL Charge 2 speaker via Bluetooth. This will also be done with two other speakers. | PASSED | Antonio Cardona & Nicole LoGiudice
3.2.1.9 | Frequency Response | The frequency range is at least from 0 - 20kHz and at most +/- 3dB using at least 10 slidable knobs. | A signal generator is connected to the input of the GrAPE, and a voltmeter is connected to the output. The frequency of the signal generator is varied over the frequency range of 0 - 20 kHz and any variation in output level is recorded. The maximum variation is set as the +/-. | UNTESTED | Nathan Finley
3.2.1.9.2 | Signal-to-Noise Ratio | The GrAPE has an SNR of at least 60 dB at maximum amplification. | A signal generator is connected to the input of the GrAPE, and a millivoltmeter is connected to the output. The signal generator is set to 1 kHz and recorded on the millivoltmeter as the signal. The input signal is then removed and the noise is recorded on the millivoltmeter. | UNTESTED | Nathan Finley
3.2.1.9.3 | Crosstalk | At most, a crosstalk of -80dB at 1 kHz. | The signal generator is connected to the input of the GrAPE. The AC millivoltmeter is connected to the audio output and the output level is recorded as the reference level. The AC millivoltmeter is then moved to the output circuit that is to be tested for crosstalk. | UNTESTED | Nathan Finley
3.2.1.9.3 | Total Harmonic Distortion | The GrAPE produces a harmonic distortion of less than or equal to 0.3%. | The signal generator is connected to the input of the GrAPE. The distortion analyzer is connected to the output and will read the THD. The test is repeated for frequencies 0, 1 kHz, 5 kHz, 10 kHz, 15 kHz, and 20 kHz. The test will be completed for minimum, no change, and maximum gain of each frequency bandwidth, left and right, and master volume. | UNTESTED | Nathan Finley
3.2.3.1.1 | Power Consumption | The total power consumption of the entire device does not exceed 12 W/hr with everything turned on. | User multimeter and oscilloscope to validate voltage and current levels connected to the battery while the GrAPE is streaming audio via Bluetooth Input to Bluetooth Output. | TESTING | Antonio Cardona
3.2.3.1.2 | Input voltage (subsystems) | The voltage levels provided to each corresponding subsystem are 3.3, 5, +/- 15 V and do not exceed a variation of +/- 0.2, 0.5, 10 V respectively. | Use multimeter to validate input voltage levels at entrance to each subsystem. (Bluetooth Receiver, Charging IC, Bluetooth Transmitter, Audio Equalizer) | PASSED | Antonio Cardona